## DVP
Senior Capstone Design
Project: | 3D Gaming Environment for Arm Assesment |  | Primary Author: | Miguel Villanueva, Alex Pena, Dawson Hill
Team: | MAD SABINO |  | Date: | 2021-10-03
Design Validation Plan & Results (DVP&R)
Requirement | Test | Test Subject | Target Date | Result | Recommendation
Virtual arm accuracy (i.e. control should follow the same physical direction) | Record inputs from SABINO and validate they are exactly replicated within the environment. | Operating BLUE SABINO with Game Build | 2021-12-05
Patient's movement shoud be responsive | Input delay test. | Operating BLUE SABINO with Game Build | 2021-12-05
The virtual environment should respond correctly with keyboard and mouse inputs. | Play test implementation | Unity Editor | 2021-11-22
The virtual environment should respond correctly with inputs from the BLUE SABINO. | Physical test + virtual environment build. | Operating BLUE SABINO with Game Build | 2021-12-05
The tasks shoud be fully customizable and configurable. | Choose a task, change/customize at least 'x' options, which should be observable. | Operating BLUE SABINO with Game Build | 2022-02-01
The display should provide clear visualization of position and orientation of on-screen items through shading from light sources, shadows, and clear contract from the background. | Move the virtual arm to some target, and the position in-game should accurately reflect the real-world position/orientation. | BLUE SABINO Display | 2022-03-01
The background should be simple and minimize distraction from the task or confusion over task targets/cues. | Play with the visuals of the gaming environment | BLUE SABINO Display | 2022-03-01
The virtual human arm should allow modular use of any of the list of joints to be controlled from robot outputs | Using the list of all available joints, perform actions with each joint individually, and in conjunction. | Operating BLUE SABINO with Game Build and Display | 2022-04-01
The end goal is to have 5 degrees of motion within the armature implemented within the software. | Stage testing. 2 degrees to 5 degrees for each joint movement | Operating BLUE SABINO with Game Build | 2022-04-17
The end product should run smoothly with a responsive and intuitive graphical interface. | Profiler test. Target 60 frames per second. | Unity Editor and Build Test with FPS counter | 2022-04-01
End product must be intutitive | Timed user test | Gaming Environment | 2022-02-15
SABINO PC must interface correctly with host PC. | Inputs are interpretted correctly back and forth. | BLUE SABINO Computing Hardware | 2021-11-22
Virtual arm(s) must be visiible from a 3rd Person view. But als not block the task space. | Manually try various tasks while moving the arm(s) around. | Gaming Environment/Virtual Arm | 2021-12-12
SABINO movement must be tracked precisely to ensure accurate repeatability. | Calibration test. | BLUE SABINO Data Collection and Gaming Environment | 2022-01-14