## DVP
Senior Capstone Design
Project: | 3D Gaming Environment for Arm Assesment |  | Primary Author: | Miguel Villanueva, Alex Pena, Dawson Hill
Team: | MAD SABINO |  | Date: | 2022-01-20
Design Validation Plan & Results (DVP&R)
Requirement | Test | Test Subject | Target Date | Result | Recommendation
Virtual arms should allow modualar use of joints (listed below), but should move in a connected manner | Single point of control test (if the hand is moved (e.g. forward), the rest of the arm should move accordingly (i.e. in a realistic fashion) | Virtual arms | 2022-01-14 | Rigged model's inverse kinematics acomplish the connected manner | Contact Jacob Wobido to see if we can acquire a model capable of having sections of the arm be transparent
Virtual arms should be controllable by the keyboard | Do the virtual arms respond correctly to the keyboard | Virtual arms | 2022-02-10 | Virtual arms move by rotations about the x,y, and z axis for the upper arm, lower arm, and hand | Get more precise movement that match the joint requirements.
1) Adduction: shoulder out, arm away from body and towards body | Can the virtual arms perform the movement while staying connected | Virtual arms | 2022-02-24 | Yes: works as intended | None
2) Extension and flexion: arm forward and backward | Can the virtual arms perform the movement while staying connected | Virtual arms | 2022-02-24 | Yes: works as intended | None
3) Internal/external rotation about the shoulder | Can the virtual arms perform the movement while staying connected | Virtual arms | 2022-02-24 | Yes: works as intended | None
4) Elbow flexion/extension | Can the virtual arms perform the movement while staying connected | Virtual arms | 2022-02-24 | Behaves strangely but works | Tweak Vector3 numbers to be more precise. Very close
5) Forarm pronation/supination | Can the virtual arms perform the movement while staying connected | Virtual arms | 2022-02-24 | This is accomplished about the hand so it does not take affect over the forearm as intended, however it works | None, as the model cannot twist the forearm without affecting the upper arm.
6) Wrist flexion/extension | Can the virtual arms perform the movement while staying connected | Virtual arms | 2022-02-24 | Bare minimum movement is there, however it still does not look quite right. | Tweak Vector3
7) wrist radial deviation (thumb towards arm) and ulnar deviation | Can the virtual arms perform the movement while staying connected | Virtual arms | 2022-02-24 | Movement is there, however it could be better | Tweak Vector3
Polish up the arms. Possibly add in joints 8) shoulder elevation and depression; 9) shoulder retration and protraction | Can the virtual arms perform the movements while staying connected | Virtual arms | 2022-03-11
Additional joints 10-15 (The hand). 10 -11) Thumb; 12-13) Index; 14-15) Middle, Ring, Pinkie | Can the virtual hands perform the movement while staying connected | Virtual arms | 2022-03-25
Simulink Simulaiton signal output connection. | Capture rotation matricies from simulaiton and use them to move the arms. Computation most likely needed | Lab setup with target computer and host computer running our Unity environment | TBD
Menus should flow seamlessly together. | Set up a document that outlines a plan to traverse and validate each | Menus | End of Project | Menus should have no way to "get stuck". There should always be a way to get out of a scene without quitting the application. | Continue implementation of menu system.
Menus should be intuitive, with visual and potentially audio cues for UI elements. | Interact with menus, ensuring each UI element has distinct feedback features. | Menus, UI elements such as buttons, sliders, etc. | Duration of project development | Every UI element needs to have some sort of user feedback mechanism built in. Current progress reflects this requirement. | Use highlighting and pressing options to indicate if a UI element is being interacted with. Potential for auditory "clicks".
Menus need to be built in a modular way. | Menus use modular elements and introducing a new menu is seamless. | Menus, UI elements such as buttons, sliders, etc. | Duration of project development | Implementing new menus should be seamless and relatively straightforward. Current progress reflects this requirement | Use tools within Unity to help aid modularity.
Menus need to report the correct parameters to the data containers. | Pass data between menu front end and report what the data container is getting. | Menu, scriptable object. | Completion of task environment | Menus will assign the correct values to the parameters in the scene. Current progress DOES NOT reflect this requirement | Use data containers to pass parameters from front end menus into the scene seamlessly.
Each completed task will have its own configuration menu | For every new task implemented, a new configuration menu will be constructed to change various parameters. | Menus, UI elements such as buttons, sliders, etc. | Completion of project, further if necessary | As we are aiming to fully complete the Point to Point task, this may be a further development initiative after we finish our project | Use Unity tools that make building menus modular and seamless.
Tasks should be highly configurable | Change the given parameters for the point to point task. Ensure they are reflected | Point to point scriptable object | 2021-01-28 | Correct values changed according to the changes given in parameters | Continue implementation of this with all tasks/within the system
Location of items should be clearly communicated on screen | Move the virtual arms to a given location on the screen. The movement should be intuitive | Goal object and virtual arm | 2021-02-02 | Lighting and material of goal object did not allow for intuitive detection of location | Change the material on objects to have metallic or plastic properties so it may reflect lights and display position correctly
Oreintation of items should be clearly communicated on screen | Move the virtual arms to a given location and orientation on the screen. The movement should be intuitive | Goal object and virtual arm | 2021-02-02 | Lighting and material of goal object did not allow for intuitive detection of orientation | Change the material on objects to have metallic or plastic properties so it may reflect lights and display position and orientation correctly.
Background of task area must be simple and not distract from the task | Perform any task, the background should not distract from the task | Point to point task | 2021-01-28 | Background with grid lighting distracted from the indivudal objects | For now, implement the background as white with no special texture or lighting
Performance should not suffer | Run the unity profiler | 3D Environment with profiler | 2021-02-18 | Unity profiler reported above 200 frames/second in editor Will be even better on build. | None. All is good!
Point-To-Point Task Complete | Run through the point-to-point task start to finish | Point to Point task in whole 3D ENV | 2021-03-08
PTP: User must go from Start to Goal. | Run through Point-To-Point task with a Start and a Goal position. | Point to Point task in 3D environment . | 2021-04-08 | Task succesfully completed with 1 iteraition from start to goal. | None
PTP: User must go from SHome, to Start, to Goal. | Run through Point-To-Point task with a Home, Start, and Goal position. | Point to Point task in 3D environment. | 2021-04-08 | Task succesfully completed with 1 iteraition from start to goal. | None